## Master Plan
Rec # | Recommendation | Action Item | Primary Owner | Co-Owner 1 | Co-Owner 2 | Co-Owner 3 | Start Month | Start Week | End Month | End Week | Ongoing Owner (if different)
1 | Enrollment Strategy | Shared enrollment planning calendar | EVC | VCEM |  |  | Aug | 3 | Aug | 4
1 | Enrollment Strategy | Strategic needs and resources | EVC |  |  |  | Sep | 2 | Sep | 3
1 | Enrollment Strategy | Strategic questions and discussions with stakeholders | EVC | VCEM |  |  | Sept | 3 | Oct | 4
1 | Enrollment Strategy | Draft enrollment strategy and implementation timeline formation | VCs |  |  |  | Nov | 1 | Nov | 4
1 | Enrollment Strategy | Presentation of draft strategy | VCs |  |  |  | Dec | 1 | Dec | 2
1 | Enrollment Strategy | Roles, responsibilities, and accountabilities of units and staff with discussions of performance metrics | VCs | HR | DEAN | DIR | Dec | 2 | Feb | 4
1 | Enrollment Strategy | Stewardship of the enrollment strategy | VCs | [7 empty] | VCs
2 | Digital Strategy Budget and Staff | Operating budget for Digital Strategy identified for FY 15 | BUDG |  |  |  | Aug | 3 | Aug | 4
2 | Digital Strategy Budget and Staff | Discussion of ongoing budget plan for Digital Strategy | VCs | CH |  |  | Sept | 2 | Sept | 4
2 | Digital Strategy Budget and Staff | Communication planning if ongoing budget requires technology fee increase and/or Digital Strategy Special Projects Fee | VCs | ITS |  |  | Oct | 1 | Oct | 4
2 | Digital Strategy Budget and Staff | Position description and recruitment of Digital Strategy Developer | DigStrat | HR |  |  | Aug | 3 | Oct | 4
3 | IT Policy, Planning, Staffing | ITS and Procurement to develop a draft phased procurement policy that describes IT purchasing policy, implementation time, noted exceptions to the policy, and communication plan | ITS | PROC |  |  | Aug | 3 | Sept | 4
3 | IT Policy, Planning, Staffing | Discussion of draft policy with key stakeholders (e.g., Deans, VCs, etc.) | ITS |  |  |  | Oct | 1 | Oct | 4
3 | IT Policy, Planning, Staffing | Refinements to policy and approval process | ITS | PROC |  |  | Oct | 4 | Dec | 2
3 | IT Policy, Planning, Staffing | Launch of IT Procurement Policy | PROC |  |  |  | Jan | 1 |  |  | PROC
3 | IT Policy, Planning, Staffing | ITS, VCs (Executive and Enrollment), and HR to discuss staffing pilot initiative, including how to mitigate risks and concerns, how to define and measure success, expectations for access to staff, and communication protocol throughout the pilot | ITS | EVC | VCEM | HR | Aug | 3 | Sept | 2
3 | IT Policy, Planning, Staffing | VCs to discuss pilot initiative with affected staff to collect questions, concerns, and contributions to metrics | ITS | EVC | VCEM | HR | Aug | 3 | Sept | 2
3 | IT Policy, Planning, Staffing | Refinements to the pilot initiative success metrics, communication norms, and list of expectations | ITS | EVC | VCEM | HR | Sept | 2 | Oct | 1
3 | IT Policy, Planning, Staffing | Staffing pilot initiative go live | ITS | EVC | VCEM |  | Oct | 1 | Apr | 1
3 | IT Policy, Planning, Staffing | ITS submits proposal to support IT audit and strategic planning process | ITS |  |  |  | Sept | 1 | Sept | 4
3 | IT Policy, Planning, Staffing | ITS audit and strategic plan completed | ITS | [5 empty] | Jan | 4
3a | IT Policy, Planning, Staffing | Presentation of proposal to purchase Intelligent Capture to Executive Vice Chancellor, Vice Chancellor for Enrollment Management, and CIO (includes benefits, estimated time and process savings, plan for use of staff time that is reclaimed); implementation of approved plan | REC | OTSS |  |  | Aug | 4 | Dec | 2
3a | IT Policy, Planning, Staffing | Presentation of outsourcing transcript processing services to Executive Vice Chancellor, Vice Chancellor for Enrollment Management, and CIO (includes estimate of staff time saved, customer satisfaction, and business impact on general fund transcript fee collection); implementation of approved plan | EVC | REC |  |  | Sept | 2 | Dec | 4
3a | IT Policy, Planning, Staffing | Presentation of document scanning and services findings from vendor consultation and estimated fees to Executive Vice Chancellor (includes description of opportunities for reclaimed physical space); implementation of approved plan | EVC | REC |  |  | Sept | 4 | Jan | 2
4 | Student Scholarship Campaign | Development of framework for fundraising campaign strategy, goals and objectives, work plan, communication plan and timeline | VCA |  |  |  | Sept | 2 | Dec | 4
4 | Student Scholarship Campaign | Input-gathering from key stakeholders (VCs, Deans, other faculty and staff) regarding the plan, messaging, supportive content and data | VCA |  |  |  | Oct | 3 | Dec | 4
4 | Student Scholarship Campaign | Back-office preparation (prospect data management, printed materials, web materials, event organization, etc.) | VCA | DigStrat | COMM |  | Jan | 1 | May | 4
4 | Student Scholarship Campaign | Campaign Kick-Off and Phases | VCA |  |  |  | Fall 2015+ | 1 | June | 4 | VCA
5 | Recruitment Council | Discussion of creation of Recruitment Council with staff | DIR |  |  |  | Aug | 3 | Aug | 4
5 | Recruitment Council | Creation of the Recruitment Council charge, initial agenda, meeting schedule, training schedule, and progress report cycle | DIR |  |  |  | Sept | 1 | Sept | 4
5 | Recruitment Council | Recruitment Council meets and continues to build out agenda for the year; determines how best to establish cross-training and shadowing | REC |  |  |  | Sept | 4 | Sept | 4
5 | Recruitment Council | First progress report to Directors | REC |  |  |  | Nov | 1 | Nov | 1
5 | Recruitment Council | First meeting with the Advising Council | REC |  |  |  | Jan | 2 | Jan | 2
6 | Blended Advising Model and NSO | Announcement and communication around New Student Orientation jointly managed by Student Life and Enrollment Management | EVC | VCEM |  |  | Sept | 1 | Sept | 4
6 | Blended Advising Model and NSO | Cross-unit coordination of plans for adjusting current professional positions as needed for academic advising role and communicating with staff; for new hire recruitment timeline; for hiring committee formation and scheduling; and discussion of roles, responsibilities, accountabilities, and success metrics | EVC |  |  |  | Sept | 1 | Oct | 4
6 | Blended Advising Model and NSO | Work with HR to finalize the advising job description(s) necessary for the professional academic advisors, and adjust any current professional advising titles or job descriptions as needed. Proceed with recruitment | EVC | DEAN |  |  | Oct | 1 | Dec | 4
6 | Blended Advising Model and NSO | Blended advising model launches with Civitas and Starfish in place, and full access to SIS for advisors | EVC |  |  |  | Jan | 1 |  |  | EVC
6 | Blended Advising Model and NSO | Discussions around an expanded role for STaR; the hiring of a dedicated Career Services advisor; the creation of an Office of Career Services; the creation of a Working Group on Organizational Outreach; and discussions of online education strategy | VCs |  |  |  | Sept | 1 | Dec | 4
7 | Professional Development Initiative | Bi-weekly Planning Committee meetings (logistics, outcomes, communications) | CoS | HR |  |  | Aug | 3 | Oct | 4
7 | Professional Development Initiative | Communication to UALR regarding the initiative | CH |  |  |  | Sept | 1 | Sept | 4
7 | Professional Development Initiative | Launch and provision of tactical professional development training and discussions | CoS | HR | TALs |  | Oct | 1 | Mar | 4
7 | Professional Development Initiative | Measurement of current level of customer service by customer-facing staff and faculty | CoS | VCs | DEAN |  | Oct | 1 | Nov | 4
7 | Professional Development Initiative | Selection of advance team for customer service training in spring 2015 | CoS | HR |  |  | Nov | 1 | Dec | 4
7 | Professional Development Initiative | Design of campus-wide customer service training and performance metrics | CoS | HR |  |  | May | 1 |  |  | CoS
8 | Strategic Initaitives Committee | Invite standing members to the Strategic Initiatives Committee | CH |  |  |  | Aug | 3 | Aug | 4
8 | Strategic Initaitives Committee | First meeting of standing members of the Strategic Initiatives Committee to create charter and to invite rotating members | EVC |  |  |  | Sept | 2 | Sept | 4
8 | Strategic Initaitives Committee | First meeting of the full Strategic Initiatives Committee to consider outstanding opportunities and/or to generate potential opportunities for review that align with enrollment framework and emerging strategy | EVC |  |  |  | Oct | 1 | Oct | 4
8 | Strategic Initaitives Committee | Due diligence for opportunities | SC-PL |  |  |  | Oct | 4 | Feb | 4
8 | Strategic Initaitives Committee | Presentation of findings and discussion | SC-PL |  |  |  | Mar | 1 | Mar | 4
8 | Strategic Initaitives Committee | Selection and communication planning | EVC | SC-PL |  |  | May | 1 | May | 4

## Master Plan Code Key
Implementation Plan and Timeline Key:
| Recommendation Number Code Values |  |  | Owner Code Values
| 1 | Enrollment Strategy | 0 | NA
| 2 | Digital Strategy Budget and Staff | 1 | CH | Chancellor/Chancellor's Office
| 3 | IT Policy, Planning, Staffing | 2 | EVC | Executive Vice Chancellor/Office of the EVC
| 4 | Student Scholarship Campaign | 3 | VCEM | Vice Chancellor for Enrollment Management
| 5 | Recruitment Council | 4 | VCA | Vice Chancellor for Advancement
| 6 | Blended Advising Model and NSO | 5 | VCFA | Vice Chancellor for Finance and Administration
| 7 | Professional Development Initiative | 6 | VCs | All four Vice Chancellors
| 8 | Strategic Initaitives Committee | 7 | CoS | Chief of Staff
|  |  | 8 | BUDG | Budget
|  |  | 9 | HR | Human Resources
| Month |  | 10 | PROC | Procurement
| 1 | Aug | 11 | ITS | Associate Vice Chancellor of IT Services
| 2 | Sept | 12 | COMM | Communications
| 3 | Oct | 13 | DigStrat | Digital Strategy
| 4 | Nov | 14 | DIR | Directors of functional units (e.g., Admissions, OTSS, Financial Aid, Bursar, etc.)
| 5 | Dec | 15 | REC | Records
| 6 | Jan | 16 | OTSS | Office of Transfer Student Services
| 7 | Feb | 17 | REC | Recruitment
| 8 | Mar | 18 | REC-CO | Recruitment Council (Admissions, OTSS, Online, International, Military, Concurrent Enrollment, Dual Enrollment)
| 9 | Apr | 19 | TALs | Training Area Leads
| 10 | May | 20 | SC-PL | Strategic Committee Project Leads
| 11 | Fall 2015+ | 21 | DEAN | Deans
Week
| 1 | 1
| 2 | 2
| 3 | 3
| 4 | 4
| 5 | 5

## Summary Business Impact
Scoring Key: | 1 None/NA | 4 Material | One Time Implementation Costs | Recurring Implementation Costs | Gross Annual Cost Savings | Risk to University | Difficulty to Implement | Notes
2 Minor
| 3 Moderate | 5 Substantial
Recommendations
1.1 | Development of an enrollment philosophy, framework and strategy |  | 1 | 1 | 4* | 2 | 3 | 4*: Enrollment growth +1500 students at $7600 in-state tuition = $11.4million ($9.7million tuition revenue based on current institutional merit/grant aid awards)
2.1 | Dedicated Digital Strategy Budget |  | $200K | $150K* | TBD | 2 | 4 | * Offset due to increased technology fee or departmental chargebacks. TBD Annual Cost Savings depends on project-level impacts on enrollment gains and ROI
2.2 | Add 1 FTE Developer |  | 1 | $75K | TBD | 2 | 4 | TBD Annual Cost Savings depends on impact on enrollment of extra capacity
3.1 | Rationalize IT Service - Purchasing |  | 1 | 1 | $200K - $400K** | 2 | 4 | * Based on Huron experience per commodity area covered
3.2 | Rationalize IT Service - Staffing |  | 1 | 1 | 3* | 3 | 4 | *Savings on staff time and wear and tear in working at cross-purposes, or in managing potential loss of critical employees without redundancy
3.3 | Rationalize IT Service - Planning |  | 5* | 1 | 4 | 2 | 4 | *Assumes IT audit plus strategic planning advisory support in a compressed timeframe
3a | Pursue University IT solutions |  | 1 | 1 | 4* | 2 | 4 | *Annual review of outsourcing options that are coordinated across enrollment units can potentially save significant staff time and costs of tools used in silos
3a.1 | Intelligent Capture Software |  | 1 | $75K/year | 2.0 FTE | 2 | 4
3a.2 | Transcript Processing (Credential Solutions) |  | 1* | 1* | .5-.75FTE | 2 | 3 | * Huron recommends increasing the transcript fee, as necessary, to maintain revenue levels, while realizing FTE savings
3a.3 | Document Services & Scanning |  | $.05-.15/image; assuming 1M pages, $50K-150K | 1 | 3* | 2 | 2 | *Opportunity cost of prime office and operations real estate dedicated to storage
4 | Design and launch fundraising for incoming student scholarships |  | 4 | 3 | 5 | 2 | 4 | *Metrics should be established to increase student enrollment, resulting in tuition & fee revenue
5.1 | Establish Recruitment Council |  | 1 | 1 | 4* | 2 | 2 | * Cost of lost tuition revenue from lack of inquiry capture, inquiry support, and management of student needs from admission to persistence
5.2 | Align Recruitment Council with retention efforts |  | 1 | 1 | 4* | 2 | 2 | * Cost of lost tuition revenue from lack of inquiry capture, inquiry support, and management of student needs from admission to persistence
6.1 | Professional Advisors - 4 FTE hires |  | 1 | $240K-$340K | $100K offset with increased retention | 2 | 4
6.2 | Procure Starfish CRM |  | $10K | $70K-$91K | 1 | 2 | 4
6.3 | Develop/update professional advising job descriptions |  | 1 | 1 | 1 | 2 | 2
7.1 | Tactical professional development initiative |  | 3 | TBD* | 4 | 2 | 3 | * Dependent on UALR decisions on what continuous training to provide and if in-house or outsourced
7.2 | Customer service training |  | ~$70,000 for advance team training | TBD* | 4 | 2 | 3 | * Dependent on UALR decisions on what continuous training to provide and if in-house or outsourced
8.1 | Create cross-functional selection committee for strategic initiatives |  | 1 | 1 | 2* | 2 | 3 | *Potential cost savings TBD due to more efficient implementation planning and reduced project "stop-starts"
8.2 | Internal project lead appointed for each selected initiative |  | 1 | 1 | 2* | 2 | 3 | *Potential cost savings TBD due to more efficient implementation planning and reduced project "stop-starts"
8.3 | Communication planning for both initial feedback and selected ideas |  | 1 | 1 | 2* | 2 | 3 | *Potential cost savings TBD due to more efficient implementation planning and reduced project "stop-starts"

## Summary Quality Impact
|  | #1 | #2 | #3 | #4 | #5 | #6 | #7 | #8
Recommendations: |  | EM Strategy | Digital Strategy | IT Strategy | Scholarship Campaign | Recruitment Council | Blended Advising | Professional Development Initiative | Strategic Initiaves Committee
Criteria: | UALR Desired Outcomes | #1: Anticipated Quality Impact Scoring 1 - 10 (1-10)
Customer Service | Quality of experience - (prompt, courteous, consistent) | 5 | 5 | 8 | 3 | 10 | 9 | 10 | 5
| Accuracy of information | 5 | 5 | 7 | 2 | 10 | 9 | 8 | 5
| Supports expansion of services | 8 | 10 | 7 | 10 | 8 | 9 | 8 | 10
| Enhances efficiency of services | 10 | 10 | 10 | 8 | 8 | 8 | 10 | 10
Convenience | Available online | 3 | 10 | 3 | 8 | 8 | 5 | 7 | 5
| Integrated/seamless process | 8 | 9 | 10 | 10 | 10 | 9 | 9 | 8
| User-friendly (student-centric) | 7 | 9 | 9 | 10 | 10 | 10 | 10 | 8
Admin Efficiency and/or Effectiveness | Empowers front-line staff | 9 | 7 | 6 | 3 | 10 | 10 | 10 | 5
| Enhances cross-functionality or coordination | 10 | 8 | 10 | 8 | 10 | 10 | 10 | 10
| Improves internal relationships | 10 | 7 | 9 | 8 | 10 | 10 | 10 | 10
| TOTAL SCORE (out of 100) | 75 | 80 | 79 | 70 | 94 | 89 | 92 | 76
Scoring Key:
| 1 to 2 | #1: None or Slight Impact
| 3 to 4 | #1: Tangential or Mild Impact
| 5 to 6 | #1: Moderate or
| 7 to 8 | #1: Material or
| 9 to 10 | #1: Substantial or Maximum Impact